## Guide
IAC INTERNSHIP PROGRAM 2023
DOCUMENT TITLE: | PROJECT SCHEDULE
Document created By: | Ankit pilankar
Document Created On: | DD-MMM-YYYY
Version: | 1
Instructions:
1. Create a project schedule based on your Work Breakdown structure
2. You may refer the 'Example' tab. Activities & Task to be included in the schedule will vary based on your selected domain
3. You may group/ expand/collapse the set of activities
4. Please rename the file as 'IAC IP23 - your Domain Name - Project Schedule - Your Full Name'
Should you face any difficulty in completing the 'Project Schedule', please refer to 'Project Planning' Workshop, https://cloudcounselage.graphy.com/sessions/Project-Planning-64af88dcb308530823e2c19f

## EXAMPLE
PROJECT PLAN
DOCUMENT VERSION: 1.0 | [6 empty] | INSTRUCTION TO USE THE PROJECT PLAN TEMPLATE: • All fields must be duly filled • The tasks/ activities listed in the template are bare minimum tasks and are not exhaustive. You will be required to add tasks/ activities based on the technology and the respective problem statement. • Clear all the sample data provided in the template. The data provided is only for reference purposes. • Mention the features you are working on the ”task name” field. • Mention the resource name who is responsible for completing a particular feature in the “assigned to” field. • Mention the start date and end date of a particular feature in the “start date” and “end date” field respectively. • Mention the time duration for completing a specific task in the “duration in days” field. • Select the current status of the feature you are working on from the drop-down list provided in the “status” field.
PROJECT NAME | student course analysis |  |  | PLEASE GO THROUGH THE INSTRUCTION SHEET PROVIDED ON THE RIGHT HAND SIDE TO GET AN UNDERSTANDING OF HOW TO USE THIS TEMPLATE.
PROJECT MANAGER | Suraj Mane
PROJECT DELIVERABLE | Job Cloud Job Portal
PROJECT SCOPE
PROJECT START DATE | 2023-11-30
PROJECT END DATE | 2024-02-10
OVERALL PROGRESS | Done
SL NO | TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION IN DAYS | STATUS
1 Initiation
| 1.1 Identify business problem |  | 2023-11-30 | 2023-12-01 | 1 | COMPLETED
| 1.3 Create a project charter |  | 2023-12-02 | 2023-12-04 | 2 | COMPLETED
| 1.4 Requirement gathering |  | 2023-12-06 | 2023-12-10 | 4 | COMPLETED
2 Planning
| 2.1 Create SRS |  | 2023-12-18 | 2023-12-20 | 2 | COMPLETED
| 2.2 Create WBS |  | 2023-12-19 | 2023-12-21 | 2 | COMPLETED
| 2.3 Create project plan |  | 2023-12-20 | 2023-12-22 | 2 | COMPLETED
3 Execution
| 3.1 Developing |  | 2024-01-01 | 2024-01-10 | 10 | COMPLETED
| 3.2 Testing |  | 2024-01-12 | 2024-01-18 | 6 | COMPLETED
| 3.3 Deployment |  | 2024-01-22 | 2024-01-30 | 8 | COMPLETED
| 4 Closure |  | 2024-02-10 | 2024-02-10 | 1 | COMPLETED